## Instructions
SIPlat — System Test Script (UAT)
User Acceptance Test matrix — whole system
Version 1.0 · 14 August 2026
Purpose | A repeatable test script covering every SIPlat portal and the mobile apps. Execute each case, set its Status, and record the actual result. The Summary tab totals results automatically.
How to use | On the 'Test Cases' tab, work top to bottom. For each row: meet the Preconditions, follow the Test Steps, compare against the Expected Result, then set Status and add notes. Put your name and the date in the last columns.
Status values | Not Run (default) · Pass · Fail · Blocked (can't run yet) · N/A (not applicable to this deployment). Use the dropdown in the Status column.
Priority | High = must pass before go-live · Medium = important · Low = nice to have. Prioritise High cases in a time-boxed run.
Type | Functional, Security, Integration, Usability or Negative — indicates what the case is probing.
Test environment | Record the environment (URL / app build) and date of the run here: ____________________________________________
Test accounts | Have one account per role ready: Super Admin, School Administrator, Teacher, Parent, Driver, Transport Manager (plus a suspended account and a custom-role user for RBAC cases).
Defects | For any Fail, log the Test ID, steps, expected vs actual and a screenshot in your defect tracker, and reference it in the Notes column.
Scope note | Covers implemented functionality across web and mobile. The subscription/billing commercial model (Connect/Plus/Complete, entitlement engine, live Stripe) is assessed separately in the Subscription Requirements Validation document and is not exhaustively tested here.

## Summary
Test execution summary
Auto-calculated from the Test Cases tab as you fill in Status.
Overall
Total test cases | 118
Pass | 0
Fail | 0
Blocked | 0
N/A | 0
Not Run | 118
Pass rate (of executed) | 0%
By area
Area | Total | Pass | Fail | Not Run | Pass %
Authentication & account security | 10 | 0 | 0 | 10 | 0%
Roles & Access Management (item 12) | 8 | 0 | 0 | 8 | 0%
Super Admin — tenants, packages & subscriptions | 7 | 0 | 0 | 7 | 0%
Super Admin — CRM, CMS, content & ops | 8 | 0 | 0 | 8 | 0%
Secure support access (impersonation, item 13) | 4 | 0 | 0 | 4 | 0%
School Admin — people, guardians & import | 6 | 0 | 0 | 6 | 0%
School Admin — calendar, attendance & behaviour | 6 | 0 | 0 | 6 | 0%
School Admin — knowledge, meals & clubs | 5 | 0 | 0 | 5 | 0%
Communications, notifications & messaging | 7 | 0 | 0 | 7 | 0%
Pupil report release (Phase 15) | 5 | 0 | 0 | 5 | 0%
Integrations & Integration Hub | 6 | 0 | 0 | 6 | 0%
Transport manager portal | 6 | 0 | 0 | 6 | 0%
Driver portal & mobile | 5 | 0 | 0 | 5 | 0%
Parent portal & app | 7 | 0 | 0 | 7 | 0%
Teacher portal & app | 5 | 0 | 0 | 5 | 0%
AI knowledge assistant | 4 | 0 | 0 | 4 | 0%
Support ticketing (item 14) | 4 | 0 | 0 | 4 | 0%
Search | 2 | 0 | 0 | 2 | 0%
Security, privacy & audit | 5 | 0 | 0 | 5 | 0%
Mobile applications (cross-cutting) | 5 | 0 | 0 | 5 | 0%
Operations & reporting (Phase 13) | 3 | 0 | 0 | 3 | 0%
TOTAL | 118 | 0 | 0 | 118 | 0%

## Test Cases
Test ID | Area / Module | Portal | Priority | Type | Test Scenario | Preconditions | Test Steps | Expected Result | Status | Actual Result / Notes | Tester | Date Tested
AUTH-01 | Authentication & account security | All / Login | High | Functional | Valid login (school admin) | A school admin account exists | 1. Open the app and go to the login page. 2. Enter a valid school-admin email and password. 3. Submit. | User is authenticated and routed to the school administration portal. | Not Run
AUTH-02 | Authentication & account security | All / Login | High | Functional | Role-based landing routing | Accounts for each role exist | 1. Log in as teacher, then driver, then transport manager, then parent (separately). | Each role lands on its dedicated portal (/teacher, /driver, /transport, /parent) — not a generic page. | Not Run
AUTH-03 | Authentication & account security | All / Login | High | Security | Invalid password rejected | A valid account exists | 1. Enter a valid email with a wrong password. 2. Submit. | Login is rejected with a generic error; no session is created. | Not Run
AUTH-04 | Authentication & account security | All / Login | High | Functional | TOTP multi-factor authentication | MFA enrolled on the account | 1. Log in with email/password. 2. Enter the current TOTP code. | Access granted only after a correct code; an incorrect code is rejected. | Not Run
AUTH-05 | Authentication & account security | All / Login | Medium | Functional | Mandatory MFA enrolment gate | Policy 'MFA required' is on; account has no MFA | 1. Log in with email/password. | Login returns an MFA-enrolment requirement and walks the user through enrolling before entry. | Not Run
AUTH-06 | Authentication & account security | All / Login | Medium | Functional | Password expiry & grace | Password expiry policy configured; password past expiry | 1. Log in with an expired password. | User is prompted to change the password now, with a 'remind me later' option while within the grace period. | Not Run
AUTH-07 | Authentication & account security | All / Login | Medium | Functional | Show/Hide password & keep me logged in | On the login screen | 1. Toggle show/hide on the password field. 2. Tick 'keep me logged in' and log in. | Password value is revealed/hidden on toggle; the extended (30-day) session is issued. | Not Run
AUTH-08 | Authentication & account security | All / Login | High | Security | Sign out everywhere revokes sessions | Logged in on two devices/browsers | 1. On device A, open Security and choose 'sign out everywhere'. 2. Refresh device B. | All other sessions are invalidated; device B must log in again. | Not Run
AUTH-09 | Authentication & account security | All / Login | Medium | Security | Rate limiting on repeated failures | — | 1. Submit many rapid failed logins for one account/IP. | Further attempts are throttled/blocked temporarily. | Not Run
AUTH-10 | Authentication & account security | All / Login | Medium | Security | Disabled/suspended account blocked | A suspended user exists | 1. Attempt to log in as the suspended user. | Login is refused with an appropriate message. | Not Run
RBAC-01 | Roles & Access Management (item 12) | School Admin | High | Functional | View roles & permissions catalogue | Logged in as School Administrator | 1. Go to Settings > Access management > Roles & permissions. | Built-in and custom roles list with grouped feature permissions, page access and CRUD matrices. | Not Run
RBAC-02 | Roles & Access Management (item 12) | School Admin | High | Functional | Create a custom role | Access management open | 1. Create a new role, set a name. 2. Tick a subset of feature permissions and pages. 3. Save. | Role is created and appears in the list; an audit entry (ROLE_CREATED) is written. | Not Run
RBAC-03 | Roles & Access Management (item 12) | School Admin | High | Functional | Clone and edit a role | At least one role exists | 1. Clone an existing role. 2. Adjust permissions and save. | Cloned role inherits then diverges; changes persist and are audited. | Not Run
RBAC-04 | Roles & Access Management (item 12) | School Admin | High | Functional | Assign a role to a user | A custom role and a user exist | 1. Open Assign roles. 2. Assign the role to a user; save. | User gains the role; enforcement applies on their next API call (web and mobile). | Not Run
RBAC-05 | Roles & Access Management (item 12) | School Admin | High | Functional | Page-gating hides removed pages | A customised role with a page removed, assigned to a test user | 1. Log in as that user. 2. Inspect the portal navigation. | Only the removed catalog page is hidden; core nav (dashboard, help, profile, notifications) remains visible. | Not Run
RBAC-06 | Roles & Access Management (item 12) | School Admin | High | Security | Fail-open for non-customised roles | A standard built-in role user | 1. Log in and inspect navigation. | Full expected navigation shows; nothing is hidden when the role was never customised. | Not Run
RBAC-07 | Roles & Access Management (item 12) | School Admin | Medium | Functional | Disable / restore-default a role | A built-in role overridden | 1. Disable a role, then restore default. | Disabled role stops granting access; restore returns platform defaults; both audited. | Not Run
RBAC-08 | Roles & Access Management (item 12) | School Admin | Medium | Security | Feature permission enforced server-side | A role lacking a permission | 1. Call/trigger an action the role can't perform. | Action is refused by the API regardless of UI state. | Not Run
SADM-01 | Super Admin — tenants, packages & subscriptions | Super Admin | High | Functional | Create a tenant (school) | Logged in as platform super admin; a package exists | 1. Create a school with name, slug, first admin and package. | School, its config, subscription and first admin are created. | Not Run
SADM-02 | Super Admin — tenants, packages & subscriptions | Super Admin | High | Functional | Suspend / reactivate / archive a tenant | A tenant exists | 1. Suspend a tenant, then reactivate, then archive. | Status transitions apply and are reflected in the tenant list; actions audited. | Not Run
SADM-03 | Super Admin — tenants, packages & subscriptions | Super Admin | High | Functional | Create / edit a package | Packages screen open | 1. Create a package (key, name, prices, AI limit, features). 2. Edit its price and save. | Package is stored and editable without a code deploy; visible on the create-tenant form. | Not Run
SADM-04 | Super Admin — tenants, packages & subscriptions | Super Admin | Medium | Functional | Activate / deactivate a package | A package exists | 1. Toggle a package inactive, then active. | Inactive packages are hidden from tenant creation; toggling works. | Not Run
SADM-05 | Super Admin — tenants, packages & subscriptions | Super Admin | Medium | Functional | Subscriptions view & renewal reminders | Subscriptions exist with renewal dates | 1. Open Subscriptions. | KPIs (due soon, overdue, pending approval) and per-row renewal/reminder labels display. | Not Run
SADM-06 | Super Admin — tenants, packages & subscriptions | Super Admin | Medium | Functional | Manual-approval override on renewal | A subscription set to manual approval | 1. Set a subscription to manual approval. 2. Approve/reject a held renewal. | Renewal holds as pending; approve/reject updates status and is audited. | Not Run
SADM-07 | Super Admin — tenants, packages & subscriptions | Super Admin | Medium | Functional | Parent revenue dashboard | Parent subscriptions exist | 1. Open Parent Revenue. | Active count, MRR/ARR/ARPU and per-school breakdown display; no card data shown (opaque references only). | Not Run
SPLT-01 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | Create & send an email campaign | Email provider configured | 1. Compose a campaign, pick an audience, send test, then send. | Audience resolves de-duped; send is recorded; open/click tracking populates the campaign report. | Not Run
SPLT-02 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | Website subscribe capture | Public site form available | 1. Submit the public 'subscribe now' form. | A CRM subscriber is created with consent; one-click unsubscribe works. | Not Run
SPLT-03 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | CMS page publish & public render | Logged in as super admin | 1. Create a CMS page (slug, SEO, body), publish. 2. Fetch the public page/API. | Draft is hidden; published page renders and is served via the public (CORS-open) API. | Not Run
SPLT-04 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | Template library share to tenants | — | 1. Create an email/message template, mark shared. | Tenant admins see shared plus their own templates; version history is retained. | Not Run
SPLT-05 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | FAQ management + bulk import | Super admin console | 1. Create/edit/publish a FAQ; run a CSV/JSON bulk import. | FAQs manage correctly; published FAQs appear in Help on web and mobile. | Not Run
SPLT-06 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | Announcement (global) with banner | — | 1. Publish a global notice with priority. | Login banner shows the top-priority notice for all roles; dismiss ≠ read; centre tracks read state. | Not Run
SPLT-07 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | Platform report generation | Data exists | 1. Generate usage/subscription/engagement reports in CSV/PDF/JSON. | Reports generate and download in each format. | Not Run
SPLT-08 | Super Admin — CRM, CMS, content & ops | Super Admin | Medium | Functional | Live email config & test | SMTP/provider keys available | 1. Set provider + from address, run send-test. | Encrypted key stored (never returned); verified badge shows on a successful test. | Not Run
IMP-01 | Secure support access (impersonation, item 13) | Super Admin / School | High | Security | Request & approve support access | A support-access-capable admin | 1. Raise a support-access request for a target user. 2. Approve it. | A time-bound, guarded impersonation session is created only after approval. | Not Run
IMP-02 | Secure support access (impersonation, item 13) | Super Admin / School | High | Security | Actions attributed to the admin | An active support session | 1. Perform an auditable action while impersonating. | Every audit entry records the impersonating admin (impersonatedBy); history shows a 'via support' indicator. | Not Run
IMP-03 | Secure support access (impersonation, item 13) | Super Admin / School | High | Security | Time-bound expiry & revoke | An active support session | 1. Wait for expiry or revoke the grant. | Impersonation stops; the admin reverts to their own session; no lingering access. | Not Run
IMP-04 | Secure support access (impersonation, item 13) | Super Admin / School | Medium | Security | Normal auth unaffected | No impersonation active | 1. Log in normally. | Standard session works; impersonation path never activates without a valid grant. | Not Run
PPL-01 | School Admin — people, guardians & import | School Admin | High | Functional | Create a pupil record | MANAGE_USERS permission | 1. Add a pupil with reference, name, year, class, indicators. | Pupil is created with a school-unique reference and appears in the list. | Not Run
PPL-02 | School Admin — people, guardians & import | School Admin | High | Functional | Link guardians & set flags | A pupil exists | 1. Add a guardian with relationship, primary/emergency, collection authorisation. | Guardian link is created with the specified flags; many-to-many supported. | Not Run
PPL-03 | School Admin — people, guardians & import | School Admin | High | Security | Guardian relationship workflow | — | 1. Create relationship, invite, guardian verifies, platform validates. | A GuardianLink is created only via this path; every transition writes a GuardianAudit row. | Not Run
PPL-04 | School Admin — people, guardians & import | School Admin | Medium | Functional | CSV import pupils with errors | Import template downloaded | 1. Import a CSV containing some invalid rows. | Valid rows import; invalid rows are reported per-row; batch history retained. | Not Run
PPL-05 | School Admin — people, guardians & import | School Admin | Medium | Functional | Emergency contacts & collectors | A pupil exists | 1. Add prioritised emergency contacts and approved collectors. | Records save and display against the pupil. | Not Run
PPL-06 | School Admin — people, guardians & import | School Admin | Medium | Functional | Amend / suspend / revoke guardian access | An active relationship | 1. Suspend then revoke a guardian relationship. | Access changes accordingly; each action audited. | Not Run
CAL-01 | School Admin — calendar, attendance & behaviour | School Admin | High | Functional | Create a calendar event with audience | MANAGE_CALENDAR | 1. Create an event scoped to a year/class with logistics. | Event saves; only the targeted audience sees it. | Not Run
CAL-02 | School Admin — calendar, attendance & behaviour | School Admin | Medium | Functional | Consent-required event | An event with consent required | 1. Create a consent-required event. | It appears as an outstanding action to targeted parents with give/decline. | Not Run
CAL-03 | School Admin — calendar, attendance & behaviour | School Admin | Medium | Functional | Homework creation | — | 1. Add homework to a class/year with a due date. | Homework shows to the correct pupils/parents. | Not Run
CAL-04 | School Admin — calendar, attendance & behaviour | School Admin | Medium | Functional | Attendance register | Teacher/admin scope | 1. Open a register, mark present/absent, save. | Marks upsert per pupil/date/session. | Not Run
CAL-05 | School Admin — calendar, attendance & behaviour | School Admin | Medium | Functional | Behaviour/reward record | — | 1. Add a reward/behaviour record for a pupil. | Record saves with points/source; guardian notified per preferences and restrictions. | Not Run
CAL-06 | School Admin — calendar, attendance & behaviour | School Admin | Medium | Functional | Calendar multi-view (parent) | Parent with children | 1. In the parent calendar switch Day/Week/Month/Quarter/Year/List. | All views render; entries are clickable and hoverable; quarter/year drill into day. | Not Run
KNOW-01 | School Admin — knowledge, meals & clubs | School Admin | Medium | Functional | Document lifecycle | MANAGE_KNOWLEDGE | 1. Create a document, move draft→approved→published. | Lifecycle transitions apply; only published + audience-matched docs reach parents. | Not Run
KNOW-02 | School Admin — knowledge, meals & clubs | School Admin | Medium | Functional | Document versioning | A published document | 1. Create a new version (supersede). | Version increments; prior version superseded; searchable body retained. | Not Run
KNOW-03 | School Admin — knowledge, meals & clubs | School Admin | Medium | Functional | Policies with acknowledgement | — | 1. Publish a policy requiring acknowledgement. | Targeted parents/teachers see it and can acknowledge; acknowledgements recorded. | Not Run
KNOW-04 | School Admin — knowledge, meals & clubs | School Admin | Medium | Functional | Meals & menus | — | 1. Add menu items with allergens/dietary tags. | Menu shows to parents with dietary/allergen filters, tagged per child. | Not Run
KNOW-05 | School Admin — knowledge, meals & clubs | School Admin | Medium | Functional | Clubs & activities | — | 1. Create a club, enrol pupils. | Club and membership save; visible to relevant parents. | Not Run
COMM-01 | Communications, notifications & messaging | School Admin / Parent | High | Functional | Targeted broadcast | MANAGE comms | 1. Compose a message targeting a class/route; send. | Per-recipient notifications created; delivery history shows counts. | Not Run
COMM-02 | Communications, notifications & messaging | School Admin / Parent | High | Security | Emergency override | Recipients with quiet hours/prefs | 1. Send an emergency broadcast. | Emergency delivers despite preferences and quiet hours. | Not Run
COMM-03 | Communications, notifications & messaging | School Admin / Parent | Medium | Functional | SMS / WhatsApp channel + consent | Parent with number; WhatsApp opt-in / SMS opt-out | 1. Send via SMS and WhatsApp. | Delivery respects consent (WhatsApp opt-in, SMS opt-out); emergencies excepted. | Not Run
COMM-04 | Communications, notifications & messaging | School Admin / Parent | Medium | Functional | Parent self-service consent | Parent app/web | 1. Set mobile number, toggle WhatsApp/SMS. | Preferences save and are audited; masked number displayed. | Not Run
COMM-05 | Communications, notifications & messaging | School Admin / Parent | Medium | Functional | Delivery report | Messages sent | 1. Open the per-channel delivery report; export CSV. | Funnel (queued→sent→delivered→read→failed) and consent snapshot display; CSV exports. | Not Run
COMM-06 | Communications, notifications & messaging | School Admin / Parent | High | Security | Directed messaging rules | Parent with a child | 1. As a parent, open messaging. | Parent can message only staff linked to their child (admins, class teachers, assigned drivers); never other parents. | Not Run
COMM-07 | Communications, notifications & messaging | School Admin / Parent | Medium | Functional | Notification preferences | Any user | 1. Set channels, categories and frequency. | Preferences save and are enforced; the 'security' category stays locked on. | Not Run
REP-01 | Pupil report release (Phase 15) | School Admin / Teacher / Parent | High | Functional | Teacher drafts & submits a report | Teacher scope | 1. As a teacher, write a pupil report and submit. | Draft is created and submitted for approval; teacher can edit only their own draft/submitted report. | Not Run
REP-02 | Pupil report release (Phase 15) | School Admin / Teacher / Parent | High | Functional | Leadership approves & schedules | A submitted release | 1. Approve and set an embargo release time. | Release moves to scheduled; child reports mirror the batch status. | Not Run
REP-03 | Pupil report release (Phase 15) | School Admin / Teacher / Parent | High | Security | Embargo hides from parents | A scheduled (future) release | 1. As a parent, look for the report before release time. | Report is not visible until the embargo passes / release now. | Not Run
REP-04 | Pupil report release (Phase 15) | School Admin / Teacher / Parent | High | Functional | Release & notify | A scheduled release at/after embargo | 1. Trigger release (auto or 'release now'). | Reports publish; parents notified via their channel preferences; first-view read receipts recorded. | Not Run
REP-05 | Pupil report release (Phase 15) | School Admin / Teacher / Parent | Medium | Security | Every transition audited | — | 1. Review the audit trail after a full cycle. | Draft/submit/approve/schedule/release/view are all audited. | Not Run
INTG-01 | Integrations & Integration Hub | School Admin | Medium | Functional | Connect an integration | MANAGE_INTEGRATIONS | 1. Connect a catalogue connector, set config. | Integration created with status and a unique webhook token. | Not Run
INTG-02 | Integrations & Integration Hub | School Admin | Medium | Functional | Field mapping & transforms | An integration exists | 1. Edit field mappings with transforms. | Mappings save; AI-suggested mappings require approval. | Not Run
INTG-03 | Integrations & Integration Hub | School Admin | Medium | Functional | Run/retry a sync | A CSV/JSON connector | 1. Run a sync; force an error; retry. | Sync-run history, logs, provenance and an error queue are produced. | Not Run
INTG-04 | Integrations & Integration Hub | School Admin | Medium | Security | Encrypted credential vault | A connector needing secrets | 1. Save a secret; view the integration. | Secret is stored encrypted and never returned in plaintext; masked hint only. | Not Run
INTG-05 | Integrations & Integration Hub | School Admin | Medium | Security | Source-of-truth write-back gate | Write-back configured | 1. Attempt a write-back. | Only allowed when supported, enabled, permitted, approved and logged. | Not Run
INTG-06 | Integrations & Integration Hub | School Admin | Medium | Functional | Behaviour ingestion via webhook | A behaviour connector token | 1. POST a signed behaviour event to the webhook. | Event matches the pupil idempotently, records provenance, notifies guardians honouring restrictions. | Not Run
TRN-01 | Transport manager portal | Transport | High | Functional | Routes, stops & vehicles | MANAGE_TRANSPORT | 1. Create a route with stops; add a vehicle. | Route/stops/vehicle save; capacity and driver assignable. | Not Run
TRN-02 | Transport manager portal | Transport | High | Functional | Generate daily journeys | Routes & profiles exist | 1. Generate AM/PM journeys for a date. | Journeys generate idempotently for the session/day. | Not Run
TRN-03 | Transport manager portal | Transport | Medium | Functional | Fleet compliance reminders | Vehicles exist | 1. Set MOT/insurance/service/tax due dates. | Due/overdue badges surface on the fleet view. | Not Run
TRN-04 | Transport manager portal | Transport | Medium | Functional | Driver profiles & assignment | Drivers exist | 1. Add licence/DBS/medical; assign to routes. | Profiles save; assignment works; last driver on a route cannot be removed. | Not Run
TRN-05 | Transport manager portal | Transport | Medium | Functional | Incident log & resolve | — | 1. Log an incident; acknowledge; resolve with a note. | Incident lifecycle transitions and resolution note persist. | Not Run
TRN-06 | Transport manager portal | Transport | Medium | Functional | Two-way office↔driver messaging | A driver exists | 1. Send a message to a driver. | Thread is delivered; unread badge updates. | Not Run
DRV-01 | Driver portal & mobile | Driver | High | Functional | View today's journeys | Driver with assigned journeys | 1. Open the driver home/journeys. | Assigned journeys and roster (with medical flags) display. | Not Run
DRV-02 | Driver portal & mobile | Driver | High | Functional | Boarding actions fire notifications | An active journey | 1. Start, board a pupil, mark absent, drop off, complete. | Each action updates status and fires the matching parent notification. | Not Run
DRV-03 | Driver portal & mobile | Driver | Medium | Functional | Vehicle pre-trip check | — | 1. Complete the walk-around; fail one item. | A failed check auto-raises a high-severity transport incident. | Not Run
DRV-04 | Driver portal & mobile | Driver | Medium | Functional | Scoped driver search | Driver with routes | 1. Search for a passenger/route/journey. | Only the driver's assigned routes, passengers and journeys are returned. | Not Run
DRV-05 | Driver portal & mobile | Driver | Medium | Functional | Offline boarding queue (mobile) | Mobile driver app, offline | 1. Record boardings offline; reconnect. | Writes queue and auto-flush on reconnect; no data loss. | Not Run
PAR-01 | Parent portal & app | Parent | High | Functional | Multi-child dashboard | Parent with 2+ children | 1. Open the parent dashboard. | Per-child cards, upcoming events/trips, homework, reports, outstanding actions across all children. | Not Run
PAR-02 | Parent portal & app | Parent | High | Security | Own-children scoping | Parent account | 1. Attempt to view another family's pupil/data. | Only the parent's own children's information is accessible; others are denied. | Not Run
PAR-03 | Parent portal & app | Parent | High | Functional | Live bus tracking (safeguarding) | Complete-level transport, child on a route | 1. Open transport tracking for the child. | Approximate location, ETA and status for own child only; no full routes/other addresses; stops on completion. | Not Run
PAR-04 | Parent portal & app | Parent | Medium | Functional | Consent give/decline | A consent-required event | 1. Give then change consent. | Consent records and updates; reflected as an outstanding action. | Not Run
PAR-05 | Parent portal & app | Parent | Medium | Functional | Menu, rewards & reports | Data exists | 1. Open menu, rewards and reports centre. | Dietary/allergen filters work; rewards honour restrictions; report centre exports PDF. | Not Run
PAR-06 | Parent portal & app | Parent | Medium | Functional | Notifications centre | Notifications exist | 1. Filter by type; mark read; deep-link. | Filters, per-item and mark-all read, and deep links to the relevant page work. | Not Run
PAR-07 | Parent portal & app | Parent | Medium | Functional | Add personal calendar entry | — | 1. Add a family calendar entry. | Personal entry shows alongside connected feeds. | Not Run
TCH-01 | Teacher portal & app | Teacher | High | Security | Scope to assigned pupils only | Teacher with class/subject/trip assignments | 1. Open My pupils; attempt to access an unassigned pupil. | Only assigned pupils are visible; unassigned returns 403. | Not Run
TCH-02 | Teacher portal & app | Teacher | High | Functional | Attendance & behaviour | Teacher scope | 1. Mark a register; log a behaviour record. | Marks and records save under the teacher's name/scope. | Not Run
TCH-03 | Teacher portal & app | Teacher | Medium | Functional | Scoped teacher search | Teacher scope | 1. Search pupils/timetable/trips/reports/behaviour. | Results are limited strictly to the teacher's scope; CSV export works. | Not Run
TCH-04 | Teacher portal & app | Teacher | Medium | Functional | Trips & headcount | Teacher on a trip | 1. Post a trip update / headcount. | Update feeds the timeline and parent notifications. | Not Run
TCH-05 | Teacher portal & app | Teacher | Medium | Security | Scoped AI assistant | Teacher scope | 1. Ask the assistant about pupils. | Answers only from assigned pupils + non-personal whole-school info; never other pupils. | Not Run
AI-01 | AI knowledge assistant | All roles | High | Security | Permission-filtered retrieval | Any role | 1. Ask a question spanning restricted data. | Retrieval is filtered by role/permission before answering; unauthorised records never surface. | Not Run
AI-02 | AI knowledge assistant | All roles | Medium | Functional | Grounded answers with citations | Documents exist | 1. Ask a policy/document question. | Answer cites source, label and date; no-guess / not-found handled honestly. | Not Run
AI-03 | AI knowledge assistant | All roles | Medium | Functional | AI drafting requires confirmation | Staff assistant | 1. Generate a draft communication. | Draft is created but nothing is issued without explicit human confirmation. | Not Run
AI-04 | AI knowledge assistant | All roles | Medium | Security | AI query audited & usage counted | — | 1. Ask several questions. | Each query is audited; AI usage counts against the plan allowance. | Not Run
TIC-01 | Support ticketing (item 14) | All / School Admin | High | Functional | Raise a ticket | Logged in | 1. Create a ticket with category, priority, severity. | Ticket created with an SH-reference; appears in the requester's list. | Not Run
TIC-02 | Support ticketing (item 14) | All / School Admin | Medium | Functional | Lifecycle & assignment | An open ticket | 1. Move through acknowledge→assign→in-progress→resolved→closed. | Nine-state lifecycle transitions correctly; SLA tracked. | Not Run
TIC-03 | Support ticketing (item 14) | All / School Admin | Medium | Functional | Internal notes & escalation | A ticket exists | 1. Add an internal note; escalate. | Internal notes hidden from requester; escalation flagged. | Not Run
TIC-04 | Support ticketing (item 14) | All / School Admin | Medium | Functional | Mobile photo attachment | Mobile app | 1. Attach a photo on a new ticket and on a reply. | Photos attach (thumbnail preview) and send; inbound attachments render as thumbnails. | Not Run
SRCH-01 | Search | All | Medium | Functional | School enterprise search | School admin | 1. Search across pupils, staff, events, docs, etc. | Grouped results across record types; CSV export works. | Not Run
SRCH-02 | Search | All | Medium | Security | Parent search scoping | Parent | 1. Search as a parent. | Only own children and applicable info returned. | Not Run
SEC-01 | Security, privacy & audit | All / Platform | High | Security | Cross-tenant isolation | Two tenants exist | 1. As tenant A, attempt to read tenant B data via API. | Access denied; every tenant query is scoped by schoolId. | Not Run
SEC-02 | Security, privacy & audit | All / Platform | High | Security | PII masking for platform staff | Pupil PII present | 1. As platform staff, view pupil data without a grant. | PII is masked unless a time-boxed, audited unmask grant is issued. | Not Run
SEC-03 | Security, privacy & audit | All / Platform | Medium | Security | Data-subject request | — | 1. Run an export and an erasure DSR. | Export bundle produced; erasure fulfilled; both audited. | Not Run
SEC-04 | Security, privacy & audit | All / Platform | Medium | Security | Retention purge | Retention configured | 1. Run the retention purge. | Data beyond retention is purged; action audited. | Not Run
SEC-05 | Security, privacy & audit | All / Platform | Medium | Security | Audit completeness | Perform varied actions | 1. Review the audit trail. | Privileged actions recorded with actor, tenant, timestamp and target. | Not Run
MOB-01 | Mobile applications (cross-cutting) | Mobile | High | Functional | Role experience selection | Accounts per role | 1. Log in on mobile as parent/teacher/driver/admin. | The correct role experience renders from the backend app role. | Not Run
MOB-02 | Mobile applications (cross-cutting) | Mobile | High | Security | Biometric unlock & keychain | Biometrics enrolled | 1. Background the app; relaunch. | Face ID / fingerprint unlock works; session stored in the device keychain. | Not Run
MOB-03 | Mobile applications (cross-cutting) | Mobile | Medium | Functional | Offline-first & sync | Any role, offline | 1. Read cached data offline; make a write; reconnect. | Cache-first reads work; queued writes auto-flush on reconnect. | Not Run
MOB-04 | Mobile applications (cross-cutting) | Mobile | Medium | Functional | Push notifications | Push credentials configured | 1. Trigger a targeted notification. | Push arrives honouring category, targeting, quiet hours and emergency override. | Not Run
MOB-05 | Mobile applications (cross-cutting) | Mobile | Medium | Functional | Assistant-first navigation | — | 1. Open each role's app. | AI Assistant leads the navigation where the role has one; standardised tabs. | Not Run
OPS-01 | Operations & reporting (Phase 13) | School Admin | Medium | Functional | Operations dashboard | Data exists | 1. Open the Operations dashboard. | Live tiles across attendance, transport, trips, engagement, AI and integrations render. | Not Run
OPS-02 | Operations & reporting (Phase 13) | School Admin | Medium | Functional | Reports export | — | 1. Generate transport/trip/engagement reports; export CSV and PDF. | Reports compute from real data and export in both formats. | Not Run
OPS-03 | Operations & reporting (Phase 13) | School Admin | Medium | Functional | Scheduled & trust roll-up | A trust/group | 1. Configure a scheduled report; view group roll-up. | Scheduled report configured; trust-level roll-up aggregates member schools. | Not Run