## Cover
SchoolHub / SIPlat — Enhancements Backlog
Spec dated 15 August 2026 · decomposed into epics & user stories for sign-off
Document | Enhancements & Improvements — product backlog
Source spec | 'Enhancements & Improvements – 15 August' (7 areas)
Version | 0.1 (draft for sign-off)
Prepared | 2026-08-15
Epics | 7
Stories | 28
Method | MoSCoW priority · T-shirt estimate (S/M/L) · surface = Web/Mobile/API
Note | E5 Messaging and E6 PDF branding EXTEND already-delivered work (Phase-2 messaging; Download Governance) — not rebuilds.
Next step | Review & sign off priorities, then implementation proceeds area-by-area.
Legend — MoSCoW
Must | Required for this release
Should | Important, not vital
Could | Desirable if time allows
Won't | Out of scope this round

## Epics
Epic | Name | Stories | Must | Should/Could | Suggested phase
E4 | CRM Campaign — Draft View | 2 | 2 | 0 | 1 (quick win)
E7 | Import/Download Navigation Warning | 2 | 2 | 0 | 1 (quick win)
E1 | Manual Data Import — new modules | 7 | 5 | 2 | 2
E2 | Role-based Import Permissions (Teachers) | 4 | 3 | 1 | 2
E6 | PDF Download Templates (branding) | 3 | 2 | 1 | 2
E3 | Super-Admin School Analytics | 6 | 5 | 1 | 3
E5 | Messaging Module Redesign | 4 | 3 | 1 | 3
| TOTAL | 28 | 22 | 6

## Backlog
Story ID | Epic | Title | User Story | Acceptance Criteria | Priority | Est. | Surface | Dependencies | Overlap / Notes | Status
ENH-IMP-01 | E1 — Manual Data Import — new modules | Clubs & Activities import | As a Super Admin, I can bulk-import Clubs & Activities so I can onboard a school without an API. | • Downloadable template matches system Club/Activity fields (name, category, schedule, capacity, staff lead, eligibility). • Upload validates headers and row data; invalid rows rejected with reasons. • Valid rows create/update records (idempotent upsert by key). • Import writes an audit entry. | Must | M | Web + API | Import framework | Extends existing Super-Admin manual import | Backlog
ENH-IMP-02 | E1 — Manual Data Import — new modules | Behaviour Records import | As a Super Admin, I can bulk-import behaviour records (merits/incidents). | • Template covers pupil ref, type, points, category, date, staff, note. • Pupil references resolve to existing pupils; unknown refs flagged. • Upsert + audit; feeds behaviour ingestion pipeline. | Must | M | Web + API | Behaviour model | Aligns with existing Behaviour ingestion slice | Backlog
ENH-IMP-03 | E1 — Manual Data Import — new modules | Class Timetables import | As a Super Admin, I can bulk-import class timetables. | • Template covers class, day, period, subject, room, teacher. • Validates against existing classes/subjects/staff; conflicts flagged. • Upsert by (class, day, period); audit. | Must | L | Web + API | Class/Subject models | New | Backlog
ENH-IMP-04 | E1 — Manual Data Import — new modules | Knowledge Base import | As a Super Admin, I can bulk-import Knowledge Base / information articles. | • Template covers title, category, body, audience/visibility, status. • Sanitises rich content on import; invalid HTML stripped. • Upsert + audit. | Should | M | Web + API | KB/CMS module | Uses existing sanitisation | Backlog
ENH-IMP-05 | E1 — Manual Data Import — new modules | Pupil Reports import | As a Super Admin, I can bulk-import pupil reports. | • Template matches Phase-15 report fields (pupil, cycle, subject/section, grades, comments). • Pupil & cycle references validated; malformed rows flagged. • Imports as draft or final per a column; audit. | Should | L | Web + API | Phase-15 Pupil Reports | New | Backlog
ENH-IMP-06 | E1 — Manual Data Import — new modules | Aligned template library + field dictionary | As an importer, I can download an accurate template with an example row and field guide for each module. | • Each module exposes a downloadable template with headers, example row, and required/optional flags. • A field dictionary documents each column, type and allowed values. • Templates are versioned and match the live schema. | Must | M | Web | ENH-IMP-01..05 | Consistency across all import modules | Backlog
ENH-IMP-07 | E1 — Manual Data Import — new modules | Unified validation & error queue | As an importer, I see row-level errors with reasons and suggested fixes before committing. | • Dry-run/preview shows counts of valid/invalid rows. • Each invalid row lists field, reason and suggested fix. • Nothing is written until the importer confirms the preview. | Must | M | Web + API | Import framework | Mirror MIS error-queue UX | Backlog
ENH-PERM-01 | E2 — Role-based Import Permissions (Teachers) | Granular import permission | As a tenant admin, I can grant an import permission to authorised Teachers via RBAC. | • New permission(s) for data import, assignable per role / TenantRole override. • Permission is per-module where appropriate. • Default: unassigned; School Admins retain full import. | Must | M | API + Web | RBAC | Extends static ROLE_PERMISSIONS + TenantRole overrides | Backlog
ENH-PERM-02 | E2 — Role-based Import Permissions (Teachers) | Teacher import scope enforcement (server) | As the platform, I ensure a teacher can only import data for pupils/classes under their responsibility. | • Server enforces scope: only assigned pupils, own classes/timetables, their pupils' clubs, behaviour and reports. • Out-of-scope rows are rejected with a clear reason. • Enforced at a single server chokepoint, not per-endpoint. | Must | L | API | ENH-PERM-01 | Model on Account-Manager scopedSchoolIds chokepoint pattern | Backlog
ENH-PERM-03 | E2 — Role-based Import Permissions (Teachers) | Teacher import UI (scoped) | As an authorised Teacher, I only see import options I'm permitted to use. | • Import UI lists only permitted modules. • Pickers pre-scope to the teacher's pupils/classes. • Clear messaging when nothing is in scope. | Must | M | Web | ENH-PERM-01/02 | New | Backlog
ENH-PERM-04 | E2 — Role-based Import Permissions (Teachers) | Scope + permission audit | As a compliance reviewer, I can see who imported what, within which scope. | • Every teacher import records actor, module, scope and row counts. • Audit is filterable by user and module. | Should | S | API | ENH-PERM-02 | Reuse audit infrastructure | Backlog
ENH-ANL-01 | E3 — Super-Admin School Analytics | Usage event capture / instrumentation | As the platform, I capture sessions, actions and feature usage needed for analytics. | • Confirm existing signals (logins, sessions) and add gaps: action events, feature-usage events, session duration. • Events are tenant-scoped and privacy-compliant (no sensitive payloads). • Backfill strategy documented for existing tenants. | Must | L | API | — | Foundational; assess what already exists before building | Backlog
ENH-ANL-02 | E3 — Super-Admin School Analytics | Per-school analytics dashboard | As a Super Admin, I can view usage analytics for each school. | • Shows total users, breakdown by role/type, active vs inactive, last login date/time. • Per-school selection; loads within budget for large tenants. • No PII beyond what the role may see. | Must | L | Web + API | ENH-ANL-01 | New Super-Admin section | Backlog
ENH-ANL-03 | E3 — Super-Admin School Analytics | Engagement metrics & trends | As a Super Admin, I can see time-on-platform, actions performed, most-used features and usage trends. | • Metrics: time spent, action counts, top features/functions, usage frequency and trend charts. • Charts are accessible and consistent with the design system. • Aggregations pre-computed/rolled-up for performance. | Should | L | Web + API | ENH-ANL-01/02 | dataviz standards apply | Backlog
ENH-ANL-04 | E3 — Super-Admin School Analytics | Analytics filters | As a Super Admin, I can filter analytics by date range, period, user, user type/role and school. | • All listed filters available and combinable. • Filter state persists across refresh. • Filters apply to both on-screen views and exports. | Must | M | Web + API | ENH-ANL-02 | Reuse usePersistentState | Backlog
ENH-ANL-05 | E3 — Super-Admin School Analytics | Analytics export — PDF | As a Super Admin, I can export analytics to a branded PDF. | • Export reflects current filters. • Branded template (logo, title, metadata, page-numbered footer). • Download is audited. | Must | M | Web + API | ENH-ANL-02, E6 | Reuse Download-Governance brandedPdf | Backlog
ENH-ANL-06 | E3 — Super-Admin School Analytics | Analytics export — Excel | As a Super Admin, I can export analytics to Excel. | • Workbook includes a metadata sheet (source/user/timestamp/filters). • Data matches the on-screen, filtered view. • Download is audited. | Must | M | Web + API | ENH-ANL-02 | Reuse xlsMetaSheet | Backlog
ENH-CRM-01 | E4 — CRM Campaign — Draft View | Draft campaign 'View' action | As a CRM user, I can View a Draft-status campaign from the Action column. | • Draft rows show a View action in the Action column. • View opens the campaign for review. • Action respects CRM permissions. | Must | S | Web | Phase-17 CRM | Small, self-contained | Backlog
ENH-CRM-02 | E4 — CRM Campaign — Draft View | Open / review / edit draft | As a CRM user, I can open, review and edit a draft campaign and save changes. | • Draft detail view is editable. • Edits save and remain in Draft until sent/scheduled. • Audit on edit. | Must | S | Web | ENH-CRM-01 |  | Backlog
ENH-MSG-01 | E5 — Messaging Module Redesign | Replace rich-text editor (web) | As a user, I have a modern, non-distorted message composer. | • Remove the current distorted editor; replace with a modern composer. • Reliable formatting (bold, italic, lists, links) with correct rendering. • Output still passes through sanitize-html (no XSS regression). | Must | L | Web | Existing messaging | Extends Phase-2 messaging; keep threads/mentions/reactions | Backlog
ENH-MSG-02 | E5 — Messaging Module Redesign | Responsive composer parity (mobile) | As a mobile user, the composer is modern and consistent with desktop. | • RN composer matches web capabilities and styling. • Attachments, mentions and send states behave consistently. • Works across common device sizes. | Must | L | Mobile | ENH-MSG-01 | RN kit components | Backlog
ENH-MSG-03 | E5 — Messaging Module Redesign | Usability & UX polish | As a user, messaging is easier and clearer to use. | • Improved formatting toolbar, drafts, send/delivery states, error handling. • Consistent desktop + mobile experience. • Accessibility checks pass. | Should | M | Web + Mobile | ENH-MSG-01/02 |  | Backlog
ENH-MSG-04 | E5 — Messaging Module Redesign | Messaging regression guard | As the team, existing messaging features keep working after the redesign. | • Threads, group chats, @mentions, replies, reactions, read receipts unaffected. • Sanitisation and attachment limits still enforced. • Covered by the system test script messaging cases. | Must | M | Web + Mobile | ENH-MSG-01 | Regression only | Backlog
ENH-PDF-01 | E6 — PDF Download Templates (branding) | PDF branding compliance audit | As the team, I have a gap list of PDF outputs not meeting branding standards. | • Enumerate all PDF outputs across portals. • Flag any missing logo, title, metadata, footer or consistent layout. • Produce a remediation list. | Must | S | Analysis | Download Governance | Most outputs already branded; this finds gaps | Backlog
ENH-PDF-02 | E6 — PDF Download Templates (branding) | Apply branded template to gaps | As a user, every downloaded PDF follows the branding standard. | • Logo + organisation branding present. • Document title and generation details (metadata) included. • Consistent, professional layout with page-numbered footer. | Must | M | Web + API | ENH-PDF-01 | Reuse brandedPdf helper | Backlog
ENH-PDF-03 | E6 — PDF Download Templates (branding) | Retrofit deep-nested export routes | As a user, exports from deep routes are branded and audited like the rest. | • Reports, policies, trust-acks, import-template, messaging-delivery exports use the branded template. • Each writes a DownloadAudit entry. • Consistent with other governed downloads. | Should | M | API | ENH-PDF-02 | The on-device pass noted earlier (sandbox depth cap) | Backlog
ENH-NAV-01 | E7 — Import/Download Navigation Warning | In-progress operation tracking | As the platform, I know when an import or download is running. | • Import and download flows expose a running/complete state. • State is reliable across the relevant screens. | Must | S | Web | — | Foundational for the warning | Backlog
ENH-NAV-02 | E7 — Import/Download Navigation Warning | Navigate-away warning | As a user, I'm warned before leaving a page with a running import/download. | • beforeunload + in-app route-change guard triggers while a process runs. • Message states leaving/refreshing may interrupt and require a restart. • Guard clears automatically on completion/cancel. | Must | M | Web | ENH-NAV-01 | Applies to both import and download | Backlog